## Slide 1: Sliabh Ban Resettlement Decant Presentation
A guide to the resettlement process
Notes: Hello and welcome to your guide to the Resettlement process for the Sliabh Ban Remedial Project . This presentation will go though a number of details in relation to where you will be moving to, approximately when you will be moving and How you will be supported by Galway city council in this process.

## Slide 2: General Information
Sliabh Ban remedial project began in quarter 4 2021. Due to the Covid 19 pandemic there has been a significant delay in the project, however with the easing of restrictions and the vaccination programme, there is now the ability for a contractor, his team and other professionals to be able to work on site to carry out this project in a safe manner
Block 4 numbers 27 to 34 will be used to accommodate households whilst their homes are being remediated.
You will be assigned a house number in this Block and it is anticipated that the remediation of your home will take approximately 12-14 weeks meaning you will live there for this time.
After the period of twelve weeks, we anticipate that all remedial works will be complete and you will be returning to your own home.
Notes: The Sliabh Ban remedial project has begun. Due to the Covid 19 pandemic there has been a significant delay in the project however with the easing of restrictions and the vaccination programme there is now the ability for a contractor, his team and other professionals to be able to work on site to carry out this project in a safe manner.
Block 4 or numbers 27 to 34 will be used to accommodate households whilst their homes are being remediated.
You will be assigned a house number in this Block and it is anticipated that the remediation of your home will take approximately 12-14 weeks, meaning you will live there for this time. You will be given a period of time in which to move into your decant unit and support to do so.
After the period of twelve weeks we anticipate that all remedial works will be complete and you will be returning to your own home.

## Slide 3: Where will I be moving?
Block 4 is the row of houses which is being used to accommodate your family whilst your home is being remediated. (This is Number 27 to number 34)
You will be moving to a house of a corresponding size in this Block, so if you live in a 4 bed house you will move to number 27. Each three bed house will be moved in sequence into a corresponding three bedroomed unit in Block four.
For those of you living in a two bed unit you will also move to these three bed units for the duration of the remediation of your home. You will have a extra room for storage of furniture or boxes that you will not need to unpack for the twelve weeks you are residing here.
Again the moves will generally happen in sequence – number 36 move to 27, Number 37 move to 28, Number 38 move to 29 etc.
Where you have a need for a ground floor unit then a this will be provided off site at Sliabh Rua which is directly beside the Sliabh Ban estate.
Between each decant numbers 27 to 34 there will a be deep cleaned by a professional cleaning company
Notes: Block 4 or Number 27– Number 34 is the row of houses which is being used to accommodate your family whilst your home is being remediated. You will be moving to a house of a corresponding size in this Block, so, for example, if you live in a 4 bedroomed house you will move to number 27 in Block 4. Each three bedroomed house will be moved in sequence into a corresponding three bedroomed unit in Block four.
For those of you living in a two bedroomed units you will also move to these three bedroomed units for the duration of the remediation of your home. You will have an extra room for storage of furniture or boxes that you will not need to unpack for the twelve weeks you are residing here.
Again the moves will generally happen in sequence – for example number 36 move to 27, Number 37 move to 28, Number 38 move to 29 etc.
Where you have a need for a ground floor unit this will be provided off site at the Sliabh Rua Estate which is directly beside the Sliabh Ban estate.
Numbers 27 to 34 and the ground floor off-site units will be deep cleaned by a professional cleaning company in between occupancies.

## Slide 4: In what order will our Houses be remediated?
The houses are being remediated on a block by block basis. The blocks are listed in the order that the houses will be remediated.
Block 8 & 7: Number 35-Number 44
Block 6 & 5: Number 45- Number 54
Block 4 is the row of houses which is being used to accommodate your family whilst your home is being remediated.(Number 27– Number 34)
Block 3: Number 19-Number 26
Block 2: Number 11- Number 18
Block 1: Number 1- Number 10
Notes: The blocks are listed in order that they will be remediated
The remediation process will begin with Block 4 in order that it is fully refurbished prior to being used as the temporary accommodation Block
Then we move across the road to Blocks 8 and 7or numbers 35 to 44 for the second phase of refurbishments.
We then move down the estate to Blocks 6 and 5 or numbers 45 to 54 for remediation
From here across the road Block 3 or numbers 19 to 26 will then be refurbished
Following this Block 2 or numbers 11 to 18 will be next
And finally Block 1 or numbers 1 through to 10 will be refurbished.

## Slide 5: Moving Dates
Sequence | Duration | Start | Completion
Phase 1. Block 4: Number 29-34 | 12 weeks | October 2021 | June 2022
Phase 2. Block 7 & 8 number 35-44 | 12 weeks | June 2022 | September 2022
Phase 3. Block 5 & 6 numbers 45-54 | 12 weeks | October 2022 | January 2023
Phase 4. Block 3 numbers 19-26 | 14 weeks | February 2022 | May 2023
Phase 5. Block 2 numbers 11-18 | 12 weeks | June 2323 | September 2023
Phase 6. Block 1 numbers 1-10 | 12 weeks | October 2023 | January 2024
Notes: This slide displays a list of approximate moving dates. These timescales are anticipated only and subject to change as the project evolves. Be aware, that the information given on this page will change and it will need to be updated regularly over the course of the project.
As you can see the process has already started and contractors are on site. The first decant is scheduled for June 2022 with the final returning decant to happen in January 2024.

## Slide 6: How will I be supported?
Galway City Council and Clúid will be supporting the Temporary Resettlement in the following ways:
A professional removals company will provide all the packing materials, dismantle and reassemble any furniture as necessary, and will remove your belongings, furniture and fridge to your temporary home. They will provide storage for your white goods and freestanding wardrobe's if necessary. They will also move you back to your home after it is remediated.
Block four will receive a deep clean by a professional cleaning company between each decant.
The gas / electricity/ Internet and TV utilities will paid for in the temporary accommodation. You are responsible for service contracts to your own home that may still stand whilst you are not living there i.e. internet package. You can either request a break in service for your tv/internet services whilst in the temporary accommodation or simply remove tv boxes/modems etc. when moving out and reconnect when you return. This is the responsibility of the tenant.
A mail redirection service will be put in place for each household for the duration that you will be living in Block 4.
You will receive a goodwill gesture of a rent reduction over the period of 14 weeks whilst you are being decanted and living in your temporary accommodation.
Your cooker and washing machine will be disconnected and reconnected we you are moving back to you home
This package is to acknowledge the disruption to your life whilst your homes are being remediated. You will receive a breakdown in writing of these supports prior to your decant.
Notes: Galway City Council and Clúid Housing association will be supporting the Temporary Resettlement or decanting process in the following ways:
A professional removals company will provide all of the packing materials, dismantle and reassemble any furniture as necessary, and will remove your belongings, furniture and fridge to your temporary home. They will provide storage for your white goods and freestanding wardrobe's if necessary. They will also move you back to your home after it is remediated.
Block four will receive a deep clean by a professional cleaning company between each decant or temporary tenancy.
The gas / electricity/ Internet and TV utilities will be paid for in the temporary accommodation. You are responsible for service contracts to your own home that may still stand whilst you are not living there i.e. internet package. You can either request a break in service for your tv/internet services whilst in the temporary accommodation or simply remove tv boxes/modems etc. when moving out and reconnect when you return
A mail redirection service will be put in place for each household for the duration that you will be living in Block 4.
You will receive a goodwill gesture of a rent reduction over the period of 14 weeks whilst you are being decanted and living in your temporary accommodation.
This package is to acknowledge the disruption to your life whilst your homes are being remediated. You will receive a breakdown in writing of these supports prior to your decant.

## Slide 7: What paperwork will I have to fill out?
You will need to fill out a letter of offer
You will receive a license agreement for your temporary property which you will need to sign
You will need to notify your Electricity and Gas companies that there will be a transfer of service to Galway City Council
We will ask you to sign a consent form so that we can manage the change over of your account into our name for a short period of time.
Please be aware of the approximate dates for decanting given above and note that should you sign a contract with a new utility service in advance of these dates you need to advise your resettlement officer and fill in a new consent form to allow for the transfer of services to Galway City Council while you are living in Block 4
Notes: There will be some paperwork that you will need to fill out as a Galway City Council tenant
A letter of offer for your temporary accommodation will be posted out to you and you will need to sign this prior to returning it.
You will receive a license agreement for your temporary property which you will need to sign and return by the given date.
You will need to notify your Electricity and Gas companies that there will be a transfer of service to Galway City Council for a 12 week period at least two months in advance of your move
We will ask you to sign a consent form so that we can manage the change over of your electricity and Gas accounts into our name for a short period of time.
Please be aware of the approximate dates for your temporary move as given previously and note that should you sign a contract with a new utility service in advance of these dates you need to advise your resettlement officer and fill in a new consent form to allow for the transfer of services to Galway City Council while you are living in Block 4

## Slide 8: How often will I see the Resettlement Officer?
Your resettlement officer will make regular home visits prior to the day of your house move.
You will receive a schedule of visits and a resettlement pack by post prior to your house move.
The purpose of the visit is to ensure that you are preparing for the impending move.
Where there are difficulties occurring then you will need to alert the resettlement officer.
Where you refuse to engage with the resettlement officer this will be considered a breach of your tenancy agreement.
Your Resettlement Officers’ role is to ensure that you have emotional support and that the services to support your house move are in place.
Notes: Your resettlement officer will make regular home visits prior to the day of your house move. You will receive a schedule of visits and a resettlement pack by post once a contractor has been appointed and the moving dates are agreed.
The purpose of the visit is to ensure that you are preparing for the impending move, that you are aware of your moving date, your removals time and you are progressing toward this deadline.
Where there are difficulties occurring then you will need to alert the resettlement officer and you will be supported to address these in a timely manner.
Where you refuse to engage with the Resettlement officer this will be considered a breach of your tenancy agreement.
Your Resettlement Officers’ role is to ensure that you have emotional support and that the services to support your house move are in place. These supports should help the process to go smoothly. This can only occur where all parties are willing to work together toward the delivery of that goal.

## Slide 9: If I am struggling how do I request more support?
Attached is a form which you will need to fill out for your Resettlement Officer to review.
This will highlight how your circumstances have changed and how and why you need extra supports.
If you have been diagnosed with a medical condition or have a condition that is deteriorating please attach a relevant consultants report.
If you, your partner or your child's mental health is deteriorating or you have been recently diagnosed with a mental health issue please attach a psychiatric report.
If you have mobility issues please attach an OT report
Your resettlement officer will contact you within ten working days to confirm that the request has been received and to outline a response.
Notes: You can see here a support request form. As we all know our life circumstances can change at any time. Should you need more support during the moving process you can simply contact your resettlement worker. You will be asked to fill out this form and attach evidence of the changes to your personal circumstances. Your Resettlement Officer will support you to address any extra needs you or your family may have.

## Slide 10: How do I make a complaint?
Fill out the attached complaint form
Send it by email to sliabhban@galwaycity.ie or post it to the Resettlement officer, Estate Management, Housing Department, City Hall, College Road, Galway.
You can also give it by hand if you wish to the Resettlement officer.
Your resettlement officer will contact you within five working days to confirm that the complaint was received and to outline the process regarding the specific complaint.
Notes: This slide shows a complaint form template. It is hoped that the Resettlement process will go smoothly for everyone however if you do have a complaint we want to hear it and the opportunity to respond accordingly. You contact your Resettlement officer to go through the complaint and if the issue cannot be revolved at this point then a form can be posted or emailed to you to fill out. Your issue will then be reviewed internally by Galway City Council and you will get an official response in writing regarding the matter.