## Slide 1: Sliabh Ban Resettlement Decant Presentation
A guide to the resettlement process
Notes: Hello and welcome to your guide to the Resettlement process for the Sliabh Ban Remedial Project . This presentation will go though a number of details in relation to where you will be moving to, approximately when you will be moving and How you will be supported by Galway city council in this process.

## Slide 2: General Information
Sliabh Ban remedial project is due to begin in quarter two 2021. This is dependent on Covid 19 and the ability for a contractor, his team and other professionals being able to work on site to carry out this project safely.
Block 4 numbers 27 to 34 will be used to accommodate households whilst their homes are being remediated.
You will be assigned a house number in this Block and it is anticipated that the remediation of your home will take approximately 12-14 weeks meaning you will live there for this time.
After the period of twelve weeks, all remedial works will be completed and you will be returning to your own home.
Notes: The Sliabh Ban remedial project is due to begin in quarter two 2021. This is dependent on Covid 19 and the ability for a contractor, his team and other professionals being able to work on site to carry out this project in a safe manner.
Block 4 or numbers 27 to 34 will be used to accommodate households whilst their homes are being remediated.
You will be assigned a house number in this Block and it is anticipated that the remediation of your home will take approximately 12-14 weeks, meaning you will live there for this time. You will be given a period of time in which to move into your decant unit and support to do so.
After the period of twelve weeks, all remedial works will be completed and you will be returning to your own home.

## Slide 3: Where will I be moving?
Block 4 is the row of houses which is being used to accommodate your family whilst your home is being remediated. (This is Number 27 to number 34)
You will be moving to a house of a corresponding size in this Block, so if you live in a 4 bed house you will move to number 27. Each three bed house will be moved in sequence into a corresponding three bedroomed unit in Block four.
For those of you living in a two bed unit you will also move to these three bed units for the duration of the remediation of your home. You will have a extra room for storage of furniture or boxes that you will not need to unpack for the twelve weeks you are residing here.
Again the moves will generally happen in sequence – number 36 move to 27, Number 37 move to 28, Number 38 move to 29 etc.
Where you have a need for a ground floor unit then a this will be provided off site at Sliabh Rua which is directly beside the Sliabh Ban estate.
Between each decant numbers 27 to 34 there will a be deep cleaned by a professional cleaning company
Notes: Block 4 or Number 27– Number 34 is the row of houses which is being used to accommodate your family whilst your home is being remediated. You will be moving to a house of a corresponding size in this Block, so, for example, if you live in a 4 bedroomed house you will move to number 27 in Block 4. Each three bedroomed house will be moved in sequence into a corresponding three bedroomed unit in Block four.
For those of you living in a two bedroomed units you will also move to these three bedroomed units for the duration of the remediation of your home. You will have an extra room for storage of furniture or boxes that you will not need to unpack for the twelve weeks you are residing here.
Again the moves will generally happen in sequence – for example number 36 move to 27, Number 37 move to 28, Number 38 move to 29 etc.
Where you have a need for a ground floor unit this will be provided off site at the Sliabh Rua Estate which is directly beside the Sliabh Ban estate.
Numbers 27 to 34 and the ground floor off-site units will be deep cleaned by a professional cleaning company in between occupancies.

## Slide 4: In what order will our Houses be remediated?
The houses are being remediated on a block by block basis. The blocks are listed in the order that the houses will be remediated.
Block 8 & 7: Number 35-Number 44
Block 6 & 5: Number 45- Number 54
Block 4 is the row of houses which is being used to accommodate your family whilst your home is being remediated.(Number 27– Number 34)
Block 3: Number 19-Number 26
Block 2: Number 11- Number 18
Block 1: Number 1- Number 10
Notes: The blocks are listed in order that they will be remediated
The remediation process will begin with Block 4 in order that it is fully refurbished prior to being used as the temporary accommodation Block
Then we move across the road to Blocks 8 and 7or numbers 35 to 44 for the second phase of refurbishments.
We then move down the estate to Blocks 6 and 5 or numbers 45 to 54 for remediation
From here across the road Block 3 or numbers 19 to 26 will then be refurbished
Following this Block 2 or numbers 11 to 18 will be next
And finally Block 1 or numbers 1 through to 10 will be refurbished.

## Slide 5: Moving Dates
Sequence | Duration | Start | Completion week ending
Contractor Appointment Timescale | 14 weeks | February 2021 | Week 18 3rd May 2021
Contingency Period | 2 -3 weeks |  | Week 20 Mid May on site
Block 4: Number 29-34 | 12 weeks | Week 21/22 May 2021 | 9th August 2021
Decant 1 :number 35-44 | 4 weeks | 16th August 2021 | 6th September 2021
Block 5 & 6: number 35-44 | 12 weeks | 13th September 2021 | 29th November 2021
Decant 2: number 45-54 | 4 weeks | 6th December 2021 Inclusive 2 week Christmas break 2022 ) | 10th January 2021
Block 7 & 8: number 45-54 | 14 weeks | 17th January 2022 | 4th April 2022
Decant 3: Number 19-26 | 4 weeks | 11th April 2022 | 9th May 2022 (Easter)
Block 3: Number 19-26 | 12 weeks | Week 20 16th May 2022 | Week 31 1st August 2022
Decant 4: Number 11-18 | 4 weeks | Week 32 8th August 2022 | Week 35 29th August 2022
Block 2: Number 11-18 | 12 weeks | Week 36 5th September 2022 | Week 47 November 21st 2022
Decant 5: Number 1-10 | 7 weeks | Week 48 November 2022 (Inclusive 2 week Christmas break 2022 ) | Week 2 9th January 2023
Block 1: Number 1-10 | 12 weeks | Week 3 January 2023 | Week 15 April 2023
Final Decant | 6 weeks | Week 16 April 2023 (Inclusive Easter break 2023) | Week 22 May 2023
Notes: This slide displays a list of approximate moving dates. These timescales are anticipated only and subject to the appointment, of a building contractor. Be aware, that the information given on this page will change and it will need to be updated regularly over the course of the project.
As you can see the process has already started and the tender for the procurement of the contractor has been published. It is anticipated that the first decant will happen in September 2021 with the final returning decant to happen in April 2023.

## Slide 6: How will I be supported?
Galway City Council and Clúid will be supporting the Temporary Resettlement in the following ways:
A professional removals company will provide all the packing materials, dismantle and reassemble any furniture as necessary, and will remove your belongings, furniture and fridge to your temporary home. They will provide storage for your white goods and freestanding wardrobe's if necessary. They will also move you back to your home after it is remediated.
Block four will receive a deep clean by a professional cleaning company between each decant.
Your gas / electricity/ Internet and TV utilities will paid for in full for the period of time you are in the Block four unit. You are responsible for service contracts to your home that may still stand whilst you are not living there i.e. internet package.
A mail redirection service will be put in place for each household for the duration that you will be living in Block 4.
You will receive a goodwill gesture of a rent reduction over the period of 14 weeks whilst you are being decanted and living in your temporary accommodation.
Your cooker and washing machine will be disconnected and reconnected we you are moving back to you home
This package is to acknowledge the disruption to your life whilst your homes are being remediated. You will receive a breakdown in writing of these supports prior to your decant.
Notes: Galway City Council and Clúid Housing association will be supporting the Temporary Resettlement or decanting process in the following ways:
A professional removals company will provide all of the packing materials, dismantle and reassemble any furniture as necessary, and will remove your belongings, furniture and fridge to your temporary home. They will provide storage for your white goods and freestanding wardrobe's if necessary. They will also move you back to your home after it is remediated.
Block four will receive a deep clean by a professional cleaning company between each decant or temporary tenancy.
Your gas / electricity/ Internet and TV utilities will be paid for in full for the period of the time that you are in your temporary accommodation. You are responsible for service contracts to your home that may still stand whilst you are not living there i.e. internet package.
A mail redirection service will be put in place for each household for the duration that you will be living in Block 4.
You will receive a goodwill gesture of a rent reduction over the period of 14 weeks whilst you are being decanted and living in your temporary accommodation.
This package is to acknowledge the disruption to your life whilst your homes are being remediated. You will receive a breakdown in writing of these supports prior to your decant.

## Slide 7: What paperwork will I have to fill out?
You will need to fill out a letter of offer
You will receive a license agreement for your temporary property which you will need to sign
You will need to notify your Electricity and Gas companies that there will be a transfer of service to Galway City Council
We will ask you to sign a consent form so that we can manage the change over of your account into our name for a short period of time.
You will need to contact your current TV and Internet providers as soon as you are aware of your moving date that you will require a break in service.
Please be aware of the approximate dates for decanting given above and note that should you sign a contract for a utility service in advance of these dates you may be liable to pay for your service costs if you have not agreed a break with your provider.
Notes: There will be some paperwork that you will need to fill out as a Galway City Council tenant
a letter of offer for your temporary accommodation will be posted out to you and you will need to sign this prior to returning it.
You will receive a license agreement for your temporary property which you will need to sign and return by the given date.
You will need to notify your Electricity and Gas companies that there will be a transfer of service to Galway City Council for a 12 week period at least two months in advance of your move
We will ask you to sign a consent form so that we can manage the change over of your electricity and Gas accounts into our name for a short period of time.
You will need to contact your current TV and Internet providers as soon as you are aware of your moving date that you will require a break in service.
Please be aware of the approximate dates for your temporary move as given previously and note that should you sign a contract for a utility service in advance of these dates you may be liable to pay for your service costs if you have not agreed a break in service with your provider.

## Slide 8: How often will I see the Resettlement Officer?
Your resettlement officer will make regular home visits prior to the day of your house move.
You will receive a schedule of visits and a resettlement pack by post prior to your house move.
The purpose of the visit is to ensure that you are preparing for the impending move.
Where there are difficulties occurring then you will need to alert the resettlement officer.
Where you refuse to engage with the resettlement officer this will be considered a breach of your tenancy agreement.
Your Resettlement Officers’ role is to ensure that you have emotional support and that the services to support your house move are in place.
Notes: Your resettlement officer will make regular home visits prior to the day of your house move. You will receive a schedule of visits and a resettlement pack by post once a contractor has been appointed and the moving dates are agreed.
The purpose of the visit is to ensure that you are preparing for the impending move, that you are aware of your moving date, your removals time and you are progressing toward this deadline.
Where there are difficulties occurring then you will need to alert the resettlement officer and you will be supported to address these in a timely manner.
Where you refuse to engage with the Resettlement officer this will be considered a breach of your tenancy agreement.
Your Resettlement Officers’ role is to ensure that you have emotional support and that the services to support your house move are in place. These supports should help the process to go smoothly. This can only occur where all parties are willing to work together toward the delivery of that goal.

## Slide 9: If I am struggling how do I request more support?
Attached is a form which you will need to fill out for your Resettlement Officer to review.
This will highlight how your circumstances have changed and how and why you need extra supports.
If you have been diagnosed with a medical condition or have a condition that is deteriorating please attach a relevant consultants report.
If you, your partner or your child's mental health is deteriorating or you have been recently diagnosed with a mental health issue please attach a psychiatric report.
If you have mobility issues please attach an OT report
Your resettlement officer will contact you within ten working days to confirm that the request has been received and to outline a response.
Notes: You can see here a support request form. As we all know our life circumstances can change at any time. Should you need more support during the moving process you can simply contact your resettlement worker. You will be asked to fill out this form and attach evidence of the changes to your personal circumstances. Your Resettlement Officer will support you to address any extra needs you or your family may have.

## Slide 10: How do I make a complaint?
Fill out the attached complaint form
Send it by email to sliabhban@galwaycity.ie or post it to the Resettlement officer, Estate Management, Housing Department, City Hall, College Road, Galway.
You can also give it by hand if you wish to the Resettlement officer.
Your resettlement officer will contact you within five working days to confirm that the complaint was received and to outline the process regarding the specific complaint.
Notes: This slide shows a complaint form template. It is hoped that the Resettlement process will go smoothly for everyone however if you do have a complaint we want to hear it and the opportunity to respond accordingly. You contact your Resettlement officer to go through the complaint and if the issue cannot be revolved at this point then a form can be posted or emailed to you to fill out. Your issue will then be reviewed internally by Galway City Council and you will get an official response in writing regarding the matter.